SEARCH FOR PARTNERS

| PROGRAMME | INTERREG IVC; Priority 1: innovation and the knowledge economy IVth Call; Deadline - 1st April 2011 |
| --- | --- |
| TITLE OF THE PROJECT | “COMPLEX CHALLENGES, INNOVATIVE CITIES” - CCIC |
| EXPRESSION OF INTEREST | If you are interested please email immediately for an expression of interest form; request no later than 15-Feb. This must be returned to us by 18-Feb. |
| THEME | Innovation, research and technology development |
| CONCEPT | CCIC will increase levels of innovation in 10-12 diverse partner-regions. By exchanging good practices they will address a set of interlinked challenges faced by all public authorities: public finance for innovation public authorities as innovators and innovation stimulators public attitudes to innovation access to innovation support public procurement to support innovation |
| PROJECT FOCUS | Partners will focus on action in (any 3 of ) the following themes: Innovative financial instruments [maybe all partners address this] Knowledge transfer Eco-innovation Public procurement Publicly owned enterprises and innovation Developing the ‘entrepreneurial mindset’ Citizen participation in innovation Regional blind-spots |
| PLANNED RESULTS | Adopt [10-12] very specific Regional Implementation Plans for innovation, that fully anticipate both the new financial realities of the EU, the objectives of the Europe 2020 and the EC’s “Innovation Union” initiative |
| METHODOLOGY | The overall project structure will be very tight; within this partners will have flexibility to work bilaterally on good practice importing. Priority will be given to the import-phase, and especially the adoption of an effective regional implementation plan that addresses all relevant actors and extends to 2020. Main targets are the key decision-makers in all relevant regional organisations. |
| WORK PROGRAMME | Months 0-9: benchmarking (round tables, maybe with expert input) and identification of good practices. Months 6-18: on-site examination of identified good practices in 2 cycles of visits Months 18-24: import of the good practices (import workshops, supported by the exporters), maybe pilot projects or experiments. Months 24-30 adoption of implementation plan (peer-reviewed) |
| CONSORTIUM | 12 (maximum) regions, 3 from each IP zone, restricted to regional leaders (eg major cities) or regional Managing Authorities. 2 (maximum) experts rigorously selected. We welcome good practice exporters as well as importers. You will involve a variety of regional stakeholders. |
| INDICATIVE PARTNER BUDGET | €140k-€180k, depending on local costs and level of participation |
| BID PREPARATION | Will be done by the Lead Partner. |
| Lead Partner | Sofia Municipality; 33, Moskovska Str., Sofia 1000, Bulgaria Dr. Nadya Nikolova, Director European Programmes and Projects Tel.: +359 2 9377 286; Fax: +359 2 9885 132, E-mail: nnikolova@sofia.bg |
| CONTACT | Katya Valkova or Tim Cordy k.valkova@sofia.bg Tim@TSC-Europe.eu +359 2 93 77 352 +44 1273 700424 |